ZoikoLogia with Kriton

Project execution roadmap

From authoritative-source data collection to a working MVP: a phased, execution-ready build plan for engineering.

Prepared for: Engineering team  |  Status: Draft for kickoff  |  Version 1.0

# Executive summary

ZoikoLogia is a governed accounting intelligence platform with an embedded AI advisor, Kriton. The 20 specification documents already produced define what the finished product must contain, but they don't sequence the work. This roadmap converts those specs into six executable phases, each with a clear goal, deliverables, and exit criteria, so engineering can start building immediately instead of re-reading the full document estate before every decision.

The guiding principle carried through every phase: nothing reaches a user until it has passed through the six-stage answer pipeline — retrieve, validate, compose, cite, classify risk, and log or escalate. Every phase below either builds a piece of that pipeline or builds the governance layer around it.

# How the 20 specification documents map to six phases

| Phase | Primary specs this phase implements |
| --- | --- |
| Phase 0 — Data foundation | ZL-T0-01 Source Library and Licensing Register |
| Phase 1 — Core pipeline | ZL-T0-03 RAG Spec, ZL-T0-05 Back-End Architecture, ZL-T0-02 Knowledge Graph |
| Phase 2 — Admin console | ZL-T2-05 Admin Governance Console, ZL-T1-02 Technical Product Requirements |
| Phase 3 — Embedded UX | ZL-T2-04 ZoikoSuite Embedded Kriton UX, ZL-T2-01 Front-End Architecture |
| Phase 4 — Safety and QA | ZL-T0-04 AI Safety and Risk, ZL-T0-10 LLM Evaluation, ZL-T0-11 QA Test Plan |
| Phase 5 — Scale and licensing | ZL-T0-12 Provider Due Diligence, ZL-T0-09 Privacy and Security |

# Phase 0 — Data foundation — authoritative source ingestion

Suggested duration: weeks 1–2   |   Team: 1 backend engineer

Goal: get real, licensed or public-domain accounting/tax content flowing into a structured, versioned store — before any AI logic is built. This is the piece every other phase depends on.

## Deliverables

- Working ingestion pipeline for HMRC manuals (UK) via the GOV.UK content API

- Working ingestion pipeline for IRS publications (US) via direct PDF download

- SourceDocument and SourceChunk tables in Postgres with jurisdiction, license status, and version metadata

- A basic word-based text chunker producing RAG-ready segments

## Exit criteria

- At least 3 full HMRC manuals and 5 IRS publications ingested and queryable in the database

- Every stored row has a traceable source_url and license_status — no unattributed content

# Phase 1 — Core six-stage answer pipeline

Suggested duration: weeks 3–6   |   Team: 2 backend engineers, 1 ML/AI engineer

Goal: build the actual retrieve, validate, compose, cite, classify-risk, log/escalate flow as a callable FastAPI service, using the sources ingested in Phase 0.

## Deliverables

- Retrieval endpoint: given a question, return the top-ranked source chunks with confidence scores

- Validation step: confirm retrieved sources are ACTIVE and not expired/superseded

- Compose step: LLM call constrained to only use retrieved source text, no open-ended generation

- Citation attachment: every generated sentence traceable back to a specific chunk

- Risk classifier: rule-based or model-based low/medium/high tagging

- Audit log: every request/response pair written to an append-only log table

## Exit criteria

- A test question against an ingested HMRC or IRS source returns a cited, risk-tagged answer end-to-end

- A question with no matching source correctly triggers a refusal, not a guess

# Phase 2 — Admin governance console

Suggested duration: weeks 7–9   |   Team: 1 backend engineer, 1 frontend engineer

Goal: give a human operator the ability to approve sources, review escalations, and see system health — the trust layer that makes Phase 1 safe to expose to real users.

## Deliverables

- Sidebar-navigated dashboard: overview, sources and licensing, escalation queue, provider register

- Source approval workflow: pending to approved to active states, with an approver identity recorded

- Escalation queue UI: reviewers can inspect flagged answers, see evidence, and approve or reject

- Metric cards: active sources, pending reviews, open escalations, license expiry countdown

## Exit criteria

- An admin can approve a newly ingested source and see it become citable by Kriton within the same session

- A high-risk answer from Phase 1 correctly appears in the escalation queue, not directly to the end user

# Phase 3 — Embedded Kriton UX

Suggested duration: weeks 10–12   |   Team: 2 frontend engineers

Goal: surface Kriton inside the actual accounting workflow (ZoikoSuite), not as a standalone chat window, per the embedded UX doctrine.

## Deliverables

- Embedded panel component showing answer, source citation, and risk badge inline in the workflow

- Context-preserving prompts: Kriton knows what screen/task the user is on

- Evidence-save action: user can attach a Kriton answer to a working paper

## Exit criteria

- A user can ask a question without leaving their current transaction entry screen and receive a governed answer inline

# Phase 4 — Safety, evaluation, and QA gates

Suggested duration: weeks 13–15   |   Team: 1 ML engineer, 1 QA engineer

Goal: prove the system is safe and accurate before wider rollout, with repeatable, versioned evaluation rather than manual spot-checks.

## Deliverables

- A benchmark question set per jurisdiction with known-correct answers and citations

- Automated scoring: citation accuracy, risk classification accuracy, refusal correctness

- Release gate: a model or prompt change cannot go live without passing the benchmark threshold

## Exit criteria

- A documented evaluation report exists for the current pipeline version, with pass/fail thresholds recorded

# Phase 5 — Licensing and jurisdiction scale-up

Suggested duration: month 4 onward, ongoing   |   Team: product/business lead plus engineering support

Goal: expand beyond free public-domain sources into licensed content (FASB, ICAEW, AICPA) and additional jurisdictions, only after Phases 0 to 4 have proven the model works end-to-end on free sources.

## Deliverables

- Business conversations with standards bodies for licensed content access

- Provider due-diligence records for any new data or model vendor

- A third jurisdiction added to the source register following the same ingestion pattern as Phase 0

## Exit criteria

- At least one paid content license secured and its content flowing through the same pipeline built in Phase 0 to 1

# Recommended tech stack

| Layer | Choice | Why |
| --- | --- | --- |
| Backend API | FastAPI (async) | Already your working environment; async fits I/O-heavy retrieval calls |
| Database | PostgreSQL | Relational integrity for source metadata; pgvector extension for embeddings later |
| Ingestion | httpx, pdfplumber, BeautifulSoup | Matches the Phase 0 skeleton already built |
| LLM layer | Provider-agnostic gateway (Claude, GPT, Gemini) | Avoids single-provider lock-in, matches ZL-T0-06 model strategy doc |
| Frontend | React | Matches the Front-End Architecture spec's component system |
| Admin dashboard | React with the sidebar pattern already prototyped | Reuse the interactive mockup structure directly |
| Background jobs | Celery or APScheduler | For scheduled source re-checks and drift detection |

# Competitive positioning: ZoikoLogia vs Thomson Reuters CoCounsel

| Dimension | Thomson Reuters CoCounsel | ZoikoLogia's opportunity |
| --- | --- | --- |
| Content moat | 175 years of licensed content, 4,500+ expert reviewers | Start narrow and free (HMRC, IRS), prove the model, license later |
| Jurisdiction coverage | US-focused, expanding internationally | UK plus US from day one, phased rollout to more |
| Admin visibility | Limited public detail on admin-side controls | Source-drift alerts, confidence-with-reasoning, license expiry tracking |
| Embedding model | Embedded in Thomson Reuters' own software suite | Embedded in ZoikoSuite, same principle, smaller footprint to start |
| Task execution | Can prepare complete, filed-ready tax returns | Longer-term roadmap item once core trust model is proven |

# Recommended first two-week sprint

Everything below uses only free, public-domain sources, so there is zero licensing dependency to start.

## Week 1

- Set up the FastAPI project skeleton with async Postgres connection

- Implement the HMRC ingestor and successfully pull one full manual (e.g. VAT Input Tax)

- Implement the IRS ingestor and successfully pull two publications

- Confirm chunking output looks reasonable on a sample document

## Week 2

- Build the retrieval endpoint: given a question, return top-matching chunks

- Wire a single LLM call constrained to only use retrieved chunks

- Add a basic citation field to the response

- Manually test 10 sample questions and record accuracy informally

By the end of week 2 you should be able to demo: a question in, a cited answer out, sourced from real HMRC or IRS content. That demo is the single most convincing artifact you can show stakeholders.

# Key risks and mitigations

| Risk | Mitigation |
| --- | --- |
| Trying to cover too many jurisdictions before the pipeline is proven | Phase 0 to 4 deliberately restricted to UK and US free sources only |
| Licensed content (FASB, ICAEW, AICPA) blocks progress | Treated as Phase 5, explicitly decoupled from earlier phases |
| Admin console scope creep before core pipeline works | Phase 2 sequenced after Phase 1, not before |
| No repeatable way to know if answer quality is improving or regressing | Phase 4 introduces a versioned benchmark before wider rollout |
| SEC or other API rate limits blocking ingestion | User-Agent header and request delay already built into the ingestion skeleton |

# Appendix: specification document reference map

| Document ID | Document name |
| --- | --- |
| ZL-OV-01 | Master Architecture and Build Doctrine |
| ZL-T1-01 | Product Requirements Document |
| ZL-T1-02 | Technical Product Requirements and Engineering Wireframe |
| ZL-T2-01 | Front-End Architecture and UX Wireframe |
| ZL-T0-05 | Back-End Architecture Specification |
| ZL-T2-04 | ZoikoSuite Embedded Kriton UX Specification |
| ZL-T0-04 | AI Safety, Risk Classification and Escalation |
| ZL-T0-13 | Event Catalog |
| ZL-T0-02 | Knowledge Graph and Accounting Ontology |
| ZL-T0-10 | LLM Evaluation and Benchmarking |
| ZL-T0-06 | LLM System Architecture and Model Strategy |
| MRP | Master Register Patch |
| ZL-T0-09 | Privacy, Security and Data Protection |
| ZL-T0-12 | Provider Due Diligence Register |
| ZL-T0-11 | QA Test Plan and Release Gate |
| ZL-T0-03 | Retrieval-Augmented Generation Specification |
| ZL-T1-08 | Learning, Practice and CPD Workspace |
| ZL-T1-09 | Review, Escalation and Audit Workspace |
| ZL-T2-05 | Admin Governance Console and Operations |
| ZL-T0-01 | Authoritative Source Library and Licensing Register |