Kriton™ Governed RAG Implementation Plan

ZoikoLogia AI Safety & Governance Platform · 13 July 2026

Recommended product direction: build and own the source governance, retrieval, safety routing, citation verification, evaluation and audit platform. Use approved OpenAI, Anthropic or open-weight models as replaceable generation providers. Do not train a foundation LLM from scratch during the initial product stages.

1. Target Architecture

Document upload

→ source registration and approval

→ parsing and normalization

→ section-aware chunking

→ embeddings and pgvector

→ licence/tenant/jurisdiction filtering

→ hybrid retrieval and reranking

→ deterministic safety route

→ approved LLM generation

→ claim-level citation validation

→ audit ledger

→ streamed frontend response

2. Guiding Principles

•	
      Policy before model: the deterministic policy engine decides whether generation may run.

•	
      No source, no answer: the model must not answer from general knowledge when eligible evidence is absent.

•	
      Tenant isolation by design: tenant boundaries must be enforced in the database and vector query.

•	
      Citations are data: citations must bind claims to canonical source chunks, not rely on free-text markers alone.

•	
      Audit before response: the durable audit record must be written before an answer is exposed.

•	
      Provider independence: OpenAI, Claude and self-hosted models must share one governed adapter contract.

Phase 0 — Stabilize the Current Foundation

Estimated effort: 2–3 days

Work

•	
      Update outdated READMEs to describe Next.js 16 and the implemented FastAPI services.

•	
      Document ENABLE_RAG_EMBEDDINGS, ENABLE_ML_CLASSIFIER, provider selection and model configuration.

•	
      Apply required disclaimers before answer validation, or split pre- and post-disclaimer checks explicitly.

•	
      Prevent generation when no eligible, grounded chunks are available.

•	
      Replace silent broad exception handling with structured events containing correlation IDs.

•	
      Add database, vector store, embedding, reranker and provider health checks.

•	
      Introduce Alembic migrations instead of relying on startup ALTER TABLE operations.

Acceptance: medium-risk answers validate correctly; no model call occurs with empty evidence; retrieval failures are traceable; setup documentation matches runtime behaviour.

Phase 1 — Canonical Source and Document Model

Estimated effort: 4–6 days

Source

└── SourceVersion

└── Document

└── DocumentChunk

└── Embedding / index record

Document fields

id, tenant_id, source_id, source_version_id, filename, object_storage_key, MIME type, checksum, parser/version, ingestion status, failure reason and timestamps.

Chunk fields

id, document_id, source_id, source_version_id, tenant_id, page/section, chunk index, text hash, token count, jurisdiction, framework, authority, licence, effective dates and index version.

Upload flow

1	
      Save and scan the file.

2	
      Create a governed Source and SourceVersion.

3	
      Create a Document with UPLOADED status.

4	
      Parse, chunk and embed it.

5	
      Store vectors with canonical SQL source IDs.

6	
      Set the document to READY only after successful indexing.

7	
      Require approval before shared sources become retrievable.

Acceptance: every vector chunk maps to a real SQL source; disabling a source removes it from retrieval; normal uploads no longer fail the licence gate with source_record_not_found.

Phase 2 — Reliable Background Ingestion

Estimated effort: 4–6 days

•	
      Move parsing and embedding into background jobs.

•	
      Use UPLOADED → PARSING → CHUNKING → EMBEDDING → INDEXING → READY/FAILED states.

•	
      Store production files in object storage.

•	
      Append to existing local indexes instead of recreating them.

•	
      Make ingestion idempotent using file checksum and index version.

•	
      Support retries and re-indexing when parser, chunker or embedding versions change.

•	
      Preserve headings, page numbers, spreadsheet cells and table structure.

Begin with 500–800 token chunks, 10–15% overlap and heading-aware boundaries. Tune using evaluation results.

Acceptance: uploads return quickly with a job ID; duplicate documents do not duplicate chunks; multiple uploads remain searchable; failed jobs are retryable.

Phase 3 — Governed Hybrid Retrieval

Estimated effort: 5–7 days

Question

→ normalize and rewrite

→ identify jurisdiction/framework/topic

→ prefilter eligible documents

→ BM25 + vector search

→ merge and deduplicate

→ cross-encoder rerank

→ confidence calculation

→ immutable SourceBundle

Mandatory prefilters

•	
      Tenant ID and visibility

•	
      Approval and source-version status

•	
      Licence and display permission

•	
      Jurisdiction and accounting framework

•	
      Effective date, freshness and authority level

Retrieval method

•	
      PostgreSQL full-text/BM25 retrieval

•	
      BGE-M3 semantic retrieval

•	
      Reciprocal Rank Fusion

•	
      BGE reranker over the top 20–30 candidates

•	
      Final selection of 5–10 non-duplicative chunks

Confidence must use retrieval scores, independent source count, authority, freshness, jurisdiction match, framework match, contradictions and query coverage—not source count alone.

Acceptance: restricted or cross-tenant content never enters prompts; exact-jurisdiction primary sources rank first; weak evidence leads to clarification or review.

Phase 4 — Real Model Gateway

Estimated effort: 4–6 days

Provider contract

ProviderAdapter.generate(GenerationRequest) → GenerationResult

The request includes governed instructions, grounded context, query, structured schema, output limit, timeout, tenant policy and correlation ID. The result includes structured content, provider/model, usage, latency, finish reason and provider request ID.

•	
      Implement asynchronous OpenAI and Anthropic adapters.

•	
      Keep Groq or a self-hosted adapter as an optional approved route.

•	
      Restrict the mock adapter to tests and local demonstrations.

•	
      Route by tenant policy, risk, data residency, evaluation status, cost, latency and context requirements.

•	
      Add timeouts, safe retries, circuit breakers, provider fallback and version pinning.

•	
      Record token usage and cost without logging raw private prompts by default.

Acceptance: production never selects mock; every model is registry-approved; provider failure safely falls back or refuses; only grounded context reaches generation.

Phase 5 — Structured Answers and Verified Citations

Estimated effort: 5–7 days

{

"summary": "...",

"claims": [{

"text": "...",

"citations": [{"chunk_id": "...", "source_id": "...", "page": 14}]

}],

"limitations": [],

"follow_up_questions": []

}

Validation

1	
      Confirm each citation exists in the final SourceBundle.

2	
      Confirm the cited chunk is display-eligible.

3	
      Verify that the passage supports the claim.

4	
      Enforce source authority, jurisdiction and effective dates.

5	
      Reject professional advice or certification language.

6	
      Attach and verify mandatory disclaimers.

7	
      Remove, refuse or escalate unsupported claims.

Acceptance: all material claims are cited; citations open exact pages/sections; fabricated references fail validation; restricted content cannot leak.

Phase 6 — Conversation and Streaming UX

Estimated effort: 5–8 days

•	
      Add Conversation, Turn, Message, Attachment, RetrievalRun, GenerationRun and Feedback entities.

•	
      Rewrite follow-up questions into standalone retrieval queries.

•	
      Maintain recent turns plus a verified compact summary instead of unbounded history.

•	
      Stream progress states: policy check, retrieval, licence validation, composition and citation verification.

•	
      Add stop/regenerate, clickable citations, source preview, feedback and follow-up suggestions.

•	
      Support project/source scope selection and clarification within one query lifecycle.

Acceptance: conversations survive reload; follow-ups retrieve correctly; streaming never exposes unvalidated final content; users can inspect refusal and escalation reasons.

Phase 7 — Evaluation and Release Gates

Estimated effort: 5–7 days initially, then continuous

Datasets

IFRS, UK GAAP, US GAAP, tax, audit, payroll, professional boundaries, academic integrity, injection attacks, cross-tenant attacks, stale standards and conflicting guidance.

Metrics

•	
      Retrieval recall@5/@10, MRR, jurisdiction match and authority precision

•	
      Citation precision/completeness, claim entailment and unsupported-claim rate

•	
      Professional-boundary violations and over-refusal

•	
      PII, secret, cross-tenant and restricted-source leakage

•	
      P50/P95 latency, provider reliability and cost per answer

Release must be blocked for any cross-tenant, PII or secret leakage; critical citation regressions; policy bypasses; or a candidate model performing worse than the active approved model.

Phase 8 — Authentication and Production Readiness

Estimated effort: 4–6 days

•	
      Implement signup fully or remove the incomplete signup promise.

•	
      Use server-issued HttpOnly, Secure, SameSite cookies.

•	
      Validate sessions rather than checking cookie existence only.

•	
      Add email verification, password reset and complete RBAC/ABAC controls.

•	
      Add malware scanning, retention/deletion jobs and upload limits.

•	
      Use managed secrets, backups, recovery procedures, metrics and alerts.

3. Suggested Delivery Schedule

Sprint

Primary deliverable

1

Stability fixes and canonical source/document schema

2

Background ingestion and reliable vector indexing

3

Governed hybrid retrieval

4

OpenAI and Claude model gateway

5

Structured claims and citation verification

6

Streaming conversation experience

7

Evaluation gates and security testing

8

Authentication and production hardening

4. First Production Slice

1	
      An administrator uploads one authoritative PDF.

2	
      A governed Source and SourceVersion are created.

3	
      The document is parsed, chunked and indexed with canonical IDs.

4	
      A user asks a question.

5	
      Tenant, licence, jurisdiction, framework and freshness filters execute.

6	
      Relevant chunks are retrieved and reranked.

7	
      An approved OpenAI or Claude model generates a structured answer.

8	
      Every material claim is validated against exact source chunks.

9	
      The user receives an answer with clickable citations.

10	
      The complete decision and evidence trace is written to the audit ledger.

5. Definition of Done

•	
      No cross-tenant or restricted-source retrieval is possible.

•	
      No answer is generated without eligible evidence.

•	
      Every factual claim maps to an exact, display-eligible source passage.

•	
      Risk classification deterministically controls generation, refusal, clarification or review.

•	
      Every provider call, retrieval result, validation outcome and response is auditable.

•	
      Provider models can be changed without replacing the governance or RAG platform.

Prepared for the ZoikoLogia Kriton™ platform. Internal reasoning-layer naming and implementation details must remain consistent with project visibility rules.